## Component Inventory
AWS Integration Capability — Component Inventory
Reference: AWS Integration Capability Reference Architecture
# | Component | Category | AWS Service | Integration Role | Used In Flow | Status | Owner | Notes | Priority
1 | AWS Lambda | Compute | Lambda | Orchestration / Processing | Steps 2,3,4,5,6 | Active |  | Python/Node.js; Serverless managed service | High
2 | AWS Step Functions | Compute | Step Functions | Workflow Orchestration | Steps 1–6 | Active |  | Drives full integration pipeline; use Map state for parallel S3 processing | High
3 | Amazon S3 | Storage | S3 | Intermediate File Storage | Steps 2,3 | Active |  | Athennian_<CorrelationId>_<Date>.json; 15-day retention lifecycle policy | High
4 | Amazon DynamoDB | Storage | DynamoDB | Config / State Store Option | Optional | Review |  | Evaluate vs SSM for timestamp storage | Medium
5 | Amazon SQS | Messaging | SQS | Decoupled Message Queue | Steps 4,5 | Active |  | Per-record publish; DLQ strategy required; visibility timeout > Lambda runtime | High
6 | Amazon SNS | Messaging | SNS | Notifications / Fan-out | Alerting | Planned |  | Alerts for failures and monitoring events | Medium
7 | Amazon EventBridge | Messaging | EventBridge | Scheduler / Event Bus | Step 1 | Active |  | 24-hour cron trigger for Step Functions | High
8 | AWS API Management | API & Integ. | API Gateway / APIM | API Exposure | External | Review |  | Used for exposing integration endpoints | Medium
9 | AWS AppConfig / Param Store | Config | SSM Parameter Store | Timestamp & Config Storage | Step 3a | Active |  | Stores last processed timestamp; prevents premature update on failure | High
10 | Amazon CloudWatch | Observability | CloudWatch | Logging, Metrics & Alerts | Step 7 | Active |  | Capture logs, errors, and pipeline metrics | High
11 | Amazon OpenSearch | Observability | OpenSearch Service | Log Search & Analytics | Optional | Planned |  | Enhanced log querying on top of CloudWatch | Low
12 | AWS Secrets Manager | Security | Secrets Manager | API Credentials Management | Steps 2,3,6 | Active |  | Store Athennian & HR Data Hub API keys | High
13 | AWS KMS | Security | Key Management Service | Encryption Key Management | Cross-cutting | Active |  | Encrypt S3, SQS, and Secrets at rest | High
14 | Certificates Manager | Security | ACM | TLS Certificate Management | Cross-cutting | Active |  | Manage TLS certs for API endpoints | Medium
15 | Cognito / EntraID SSO | Identity | Cognito + EntraID | Authentication & SSO | Access Control | Active |  | JnJ EntraID SSO federated into Cognito | High
16 | AWS Mgmt Console | Management | Management Console | Operations / Visibility | Cross-cutting | Active |  | Primary ops interface for monitoring and troubleshooting | Medium
Status Legend: | Active | Planned | Review

## Process Flow Tracker
J&J AWS Integration — Process Flow Step Tracker
Step | Description | AWS Component(s) | Input | Output | Risk / Consideration | Status | Notes
1 | EventBridge triggers Step Functions every 24hrs | EventBridge, Step Functions | Cron schedule | Step Function execution | Ensure schedule is configurable; add timezone awareness | Active
2 | Lambda pulls Athennian user data via GraphQL w/ pagination | Lambda, S3 | GraphQL API (Athennian) | S3 JSON files (batch=800) | Circuit breaker needed; Lambda 15-min timeout risk at scale | Active | Filter: non-empty WWID only; 100 rec/call limit
2a | Filter & collect Athennian users with non-empty WWIDs | Lambda | Athennian API response | Filtered WWID list | Null/empty WWID handling must be explicit | Active
2b | Group records; write to S3 at batch of 800 | Lambda, S3 | WWID list | S3 file (Athennian_<CorrID>_<Date>.json) | Batch size configurable via SSM | Active | Continue until pagination = 0
3 | Lambda processes S3 files; fetches HR Data Hub delta | Lambda, S3, SSM, HR Data Hub API | S3 files + last timestamp | Delta records | Timestamp must NOT update if Lambda fails mid-run | Active
3a | Read last processed timestamp from config store | SSM Parameter Store | SSM key | Timestamp value | Atomic update — only write new timestamp on full success | Active
3b | Read S3 files one-by-one; batch WWIDs | Lambda, S3 | S3 JSON files | WWID batches | Handle missing/corrupt files gracefully | Active
3c | Call HR Data Hub API with WWIDs + timestamp | Lambda, HR Data Hub API | WWID batch + timestamp | Delta change records | 1,000 rec/page; paginate all pages before compare | Active
4 | Lambda publishes each delta record to SQS individually | Lambda, SQS | Delta records | SQS messages | Per-record publish; set message deduplication ID for idempotency | Active
5 | Separate Lambda consumes SQS messages | Lambda, SQS | SQS message | GraphQL mutation payload | Visibility timeout > Lambda execution time | Active | DLQ needed
6 | Lambda upserts HR Data Hub data into Athennian via GraphQL mutation | Lambda, Athennian API | GraphQL mutation | Upsert confirmation | Idempotency on upsert mutation required | Active
7 | Logs, errors, and alerts captured | CloudWatch, SNS | Lambda logs + metrics | Alerts / dashboards | Define alarm thresholds; tie CorrelationId to Step Functions exec ID | Active

## Risk Register
AWS Integration — Risk & Consideration Register
# | Risk / Consideration | Affected Component | Impact | Likelihood | Mitigation | Status
1 | Lambda timeout at scale | Lambda (Athennian pagination) | High | Medium | Add circuit breaker / max iteration cap; monitor execution duration in CloudWatch | Open
2 | Timestamp premature update on failure | SSM Parameter Store, Lambda | High | Medium | Only write new timestamp after full successful run; use Step Functions catch/rollback | Open
3 | SQS visibility timeout too short | SQS, Lambda | High | Low | Set visibility timeout > Lambda max execution time; configure DLQ for failed messages | Open
4 | No idempotency on Athennian upsert | Lambda, Athennian API | Medium | Medium | Use mutation deduplication key; test re-delivery scenarios | Open
5 | Runaway pagination loop | Lambda (Athennian) | High | Low | Implement max iteration cap; alert on iterations exceeding threshold | Open
6 | S3 lifecycle policy not automated | S3 | Low | Medium | Define S3 Lifecycle rule for 15-day archive retention; do not rely on manual cleanup | Open
7 | Missing DLQ strategy | SQS | High | Medium | Define DLQ per queue; set max receive count; create alarm on DLQ depth > 0 | Open
8 | CorrelationId not tied to Step Functions exec ID | CloudWatch, Step Functions | Medium | Medium | Pass execution ID as CorrelationId into Lambda context at Step 1 | Open
9 | HR Data Hub pagination incomplete | Lambda, HR Data Hub API | High | Low | Paginate ALL pages (1,000 rec/page) before processing; do not process partial datasets | Open
10 | Athennian WWID field empty edge cases | Lambda | Medium | Low | Explicit null/empty string check; log skipped records to CloudWatch | Open